## Sheet1
Task	Subtask	Estimated time	12/20/15	12/27/15	01/03/16	01/10/16	01/17/16	01/24/16	01/31/16	02/07/16	02/14/16	02/21/16	02/28/16	03/06/16	03/13/16	03/20/16	03/27/16	04/03/16	04/10/16	04/17/16	04/24/16	05/01/16	05/08/16	05/15/16	05/22/16	05/29/16	06/05/16	06/12/16	06/19/16	06/26/16	07/03/16	07/10/16	07/17/16	07/24/16	07/31/16	08/07/16	08/14/16	08/21/16
Literature search		1m
	Energy efficient vehicle control	7d
	Evolutionary Robotics/ / Evolutionary Algorithms	7d
	Reality Gap	7d
	Non-linear system identification/ / Surrogate modeling	7d
Milestone 1 (02/14/2016): / - Finished literature search / Deliverables: / - Annotated bibliography containing / top papers
Set up test tracks		8d
	Find usable tracks	3d
	Collect leverage (and GPS) data	5d
Prepare Experiments		3d
	Specify benchmark criteria	2d
	Choose algorithms to compare	1d
Milestone 2 (03/06/16): / - Preparations for experiments done / Deliverables: / - Set of test tracks / - Benchmarking system
Create motor model from real world data		7d
	Collect motor data	2d
	Learn model out of data	5d
Milestone 3 (03/20/16): / - Created motor model / Deliverables: / - Motor model
Implement algorithms		13d
	Standard NEAT	4d
	NEAT with developed motor model	2d
	NEAT with reality gap extensions	4d
	Other previously identified algorithms	3d
Create vehicle controller		7d
	Perform algorithms to create controllers	5d
	Make controllers run on vehicle	2d
Milestone 4 (05/01/16): / - Controller creation done / Deliverables: / - Controller for each algorithm
Perform experiments		9d
	Run vehicle with different controllers on test tracks	5d
	process collected data	2d
	Compare data / - Reality vs Simulation results / - Influence of different motor model / - Influence of reality gap extension	2d
Milestone 5 (05/22/16): / - Experiments performed and analyzed / Deliverables: / - Performances of controllers / - Results of comparisons
Write report		1m
Improve report based on feedback		14d
Milestone 5 (07/03/16): / - Done with report / Deliverables: / - Finished report

Mit Hardware vertraut machen
Nach Experimenten Modell anpassen / Loop einbauen